## Slide 1: Encapsulation for Drug Delivery
31st July
iGEM Team 2009
Charles
Dave
Dineka
James
Kun
Nuri
Royah
Tianyi

## Slide 2: The Project
Problem
Module 1
Module 2
Module 3
Module 4 & 5
Mod. & Test.
Summary
Overview
“Auto-encapsulation of protein drugs for release in the small intestine.”

## Slide 3: Overview of Modules
Problem
Module 1
Module 2
Module 3
Module 4 & 5
Mod. & Test.
Summary
Overview
Module 1:
Compound Production
START
Grow cells
Check
M1: Compound Production
Check
M2: Encapsulation
M3: Killing
Module 2:
Encapsulation
Module 3:
Genomic Neutralisation

## Slide 4: Gantt Chart
ACTIVITIES | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10
MIT Project description |  |  |  |  |  |  | 
Assay Protocols |  |  |  |  |  |  | 
Cloning strategy |  |  |  |  |  |  | 
Genetic Circuits |  |  |  |  |  |  | 
Biobricks |  |  |  |  |  |  | 
Genes to PCR |  |  |  |  |  |  | 
Wet lab plan |  |  |  |  |  |  | 
Gantt Chart |  |  |  |  |  |  | 
Dry lab plan |  |  |  |  |  |  | 
Order genes |  |  |  |  |  |  | 
Order Biobricks |  |  |  |  |  |  | 
Start Wet Lab |  |  |  |  |  |  | 
Timer |  |  |  |  |  |  | 
M1+Timer integration |  |  |  |  |  |  | 
M2 |  |  |  |  |  |  | 
M3 |  |  |  |  |  |  | 
Start Dry Lab |  |  |  |  |  |  | 
Genes delivered |  |  |  |  |  |  | 
Biobricks delivered |  |  |  |  |  |  | 
 | Complete
 | In progress
 | To do
 | Unknown
Summary
Overview
Module 1
Module 2
Module 3
Module 4 & 5
Mod. & Test.
Problem

## Slide 5: Module 1: Compound Production

## Slide 6: M1 Progress Report
P(arabinose)
Protein of Interest
Arabinose inducible.
Cellulase BioBricked.
PAH BioBricked.
Cloning strategy formulated.
Module 2
Module 3
Module 4 & 5
Mod. & Test.
Summary
Module 1
Overview
Problem

## Slide 7: Module 2: Encapsulation

## Slide 8: M2 Progress Report
TetR Repressible.
5 genes BioBricked.
Cloning strategy formulated.
P(TetR)
P(TetR)
RcsB
B3023
Waal Ligase
OtsA
OtsB
Module 2
Overview
Module 1
Problem
Module 3
Module 4 & 5
Mod. & Test.
Summary

## Slide 9: Module Integration
P(TetR)
LacI
P(LacI)
TetR
P(arabinose)
P(TetR)
RcsB
B3023
Waal Ligase
OtsA
OtsB
Protein of Interest
IPTG
Series of inverters
Tuneable timer – 3 potential inputs
Module 2
Overview
Problem
Module 3
Module 4 & 5
Mod. & Test.
Summary
Module 1

## Slide 10: Module Integration
Testing
Module 2
Overview
Problem
Module 3
Module 4 & 5
Mod. & Test.
Summary
Module 1
aTc

## Slide 11: Module 3: Genomic Neutralisation

## Slide 12: Overall Specifications
Module 1
Module 2
Module 3
Module 4 & 5
Mod. & Test.
Summary
Problem
Overview
Module 3
High killing rate
Failsafe mechanism
Neutralise genomic material
Limit protease degradation of our product
Non-toxic
Fast

## Slide 13: The system
Use restriction enzymes (REs) and constitutive methylation of DNA.
Encapsulation limits the induction mechanisms – chemical inducers will not be effective – place under control of a thermo-inducible system
Raise temperature to ~42°C to induce ‘killing’.
  We would have to culture our cells at ~28°C.
Module 3
Overview
Module 1
Module 2
Problem
Module 4 & 5
Mod. & Test.
Summary

## Slide 14: The system
Module 3
Overview
Module 1
Module 2
Problem
Module 4 & 5
Mod. & Test.
Summary
BBa_K098995 [Harvard ‘08]
No BB
RBS
Cl T°sensitive
T
T
λcI
RBS
DpnI
RBS
TaqI
RBS
Dam
No BB
Strong, constitutive
Weak, constitutive
J23103
J23114

## Slide 15: Problem
Harvard’s BioBrick is leaky – this is not an option for us; we don’t want to kill our cells early.
Module 3
Overview
Module 1
Module 2
Problem
Module 4 & 5
Mod. & Test.
Summary

## Slide 16: Potential Solutions
1) Use native λ pL or pR promoters – obtain sequences for these and make our own.
Altered temperature induction sensitivity of the lambda pR/cI857 system for controlled gene E expression in Escherichia coli
Wolfgang Jechlinger*, Michael P. Szostak1, Angela Witte and Werner Lubitz
At 36°C bacteria grow normally, no lysis detected; at 42°C lysis occurs after 15 min.
2) Use a commercial system – these are available and reliable.
Module 3
Overview
Module 1
Module 2
Problem
Module 4 & 5
Mod. & Test.
Summary
Plasmid | Composition | Selection Marker
pAWJ | cI857–λ pRmut(41C)–E | Tet

## Slide 17: Genetic Circuit
P(TetR)
LacI
P(LacI)
TetR
IPTG
P(arabinose)
P(TetR)
RcsB
B3023
Waal Ligase
OtsA
OtsB
Protein of Interest
DpnI
Const - Strong
CI
P(CI)
DpnI
Const - Weak
TaqI
Temperature
M1
M2
M3

## Slide 18
Timer Model
LacI
P(LacI)
TetR
IPTG
P(arabinose)
Protein of Interest

## Slide 19: Switch

## Slide 20: Delay Mechanism

## Slide 21: Biobricks
Module | Biobrick | Available? | Size (bp) | Schematic
1 (1.1) | N/A | Clones | 1500 | 
1 (1.2) | N/A | Clones | 2550 | 
2 (2.1) | N/A | PCR/ Synthesise | 792 | 
2 (2.2) | N/A | PCR/ Synthesise | 624 | 
2 (2.3) | N/A | PCR | 1401 | 
2 (2.4) | N/A | PCR | 1566 | 
2 (2.5) | N/A | PCR/ Synthesise | 753 | 
Module 2
Overview
Problem
Module 3
Module 4 & 5
Mod. & Test.
Summary
Module 1

## Slide 22: Biobricks
Module 3
Overview
Problem
Module 4 & 5
Mod. & Test.
Summary
Module | Biobrick | Available? | Size (bp) | Schematic
Timer (T.1) | BBa_Q04121 | A W (09 – KP1) | 1370 | 
Timer (T.2) | BBa_Q04400 | A W (09 – KP1) | 902 | 
3 (3.1) | BBa_K098995 | A W (09 – KP1) | 935 | 
3 | Synthesise |  | 1566 | 
3 | PCR/ Synthesise |  | 844 | 
Module 2
Module 1
Module 2

## Slide 23: Wet Lab Plan

## Slide 24: Cloning Strategy
Overview
Module 1
Module 2
Module 3
Module 4 & 5
Summary
Problem
Mod. & Test.

## Slide 25
BioBricks and Plasmids

## Slide 26: Testing

## Slide 27: Testing Strategy
We aim to:
Characterise promoters.
Test individual genes for functionality.
Test constructs (operon).
Test integrated constructs (e.g. M1-M2).
Integrate testing with cloning strategy to minimise ligations.
Overview
Module 1
Module 2
Module 3
Module 4 & 5
Summary
Problem
Mod. & Test.

## Slide 28: Checklist
Summary
Overview
Module 1
Module 2
Module 3
Module 4 & 5
Mod. & Test.
Problem
Weekly Aims:
MIT Project description
Assay Protocols
Cloning Strategies
Genetic circuits
Biobricks
Genes to PCR
Wet lab plan

## Slide 29: Checklist
Summary
Overview
Module 1
Module 2
Module 3
Module 4 & 5
Mod. & Test.
Problem
Week 5 Aims:
Lab induction & safety
Lab prep
Design primers
Orders (genes, clones, primers, assays)
Assemble timer (test?)

## Slide 30: Summary
Modular solution for the oral delivery of peptide drugs
Module 1 - Compound Production
Module 2 – Encapsulation
Module 3 – Genomic Neutralisation
Summary
Overview
Module 1
Module 2
Module 3
Module 4 & 5
Mod. & Test.
Problem